## Law
PROVINCIAL
LAW, P.A AND PROSECUTION DEPARTMENT
( Rs. in million )
Gen. S.No. | UID | Sector / Sub-sector / Name of Scheme | Location of Scheme/ District | Status Date of Approval | Target Date for Comple- tion | Estimated Cost | Actual Expenditure upto June, 21 | Revised Allocation 2021-22 |  | Estimated Expendit-ure upto June' 22 | Throw- forward as on 01-07-22 | Allocation for 2022-23 |  |  | Revised Allocation for 2022-23 |  |  | Re-Appropration 2022-23 |  |  |  | Out Side Budget |  | Overall Saving |  | Final Budget 2022-23 |  |  | Release 2022-23 |  |  | 1% TPM Charges | Expenditure |  |  | Remarks | Date of Releases | FPA
[18 empty] | Capital | Capital | Revenue | Revenue
[8 empty] | Total | F.P.A. |  |  | Capital | Revenue | Total | Capital | Revenue | Total | Addition | Deduction | Addition | Deduction | Capital | Revenue | Capital | Revenue | Capital | Revenue | Total | Capital | Revenue | Total |  | A/C | Regular | Total
1 | 2 | 3 | 4 | 5 | 6 | 5 | 8 | 9 | 10 | 11 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
JUDICIAL
Government Servant Housing
(On-Going Schemes)
1550 | LPDJD-PP-14-0046 | Construction of Staff Colony of Circuit Court Larkana | Larkano | Approved 26.12.14 (U/R) | June-23 | 150.12 | 97.594 | 52.526 | 0 | 150.12 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1551 | LPDJD-PP-19-0194 | Construction of Residential & Studio Apartments at Bath Island Bungalows No. 2,3 & 4 Karachi (SDG # 16) (Revised) | Karachi | Approved 10.03.20 | June-23 | 842.522 | 687.057 | 68.191 | 0 | 755.248 | 87.274 | 0 | 87.274 | 87.274 | 0 | 87.274 | 87.274 | [8 empty] | 0 | 87.274 | 87.274 |  | 87.274 | 87.274 |  | 0 | 0 | 0 |  | R:18-05-2023 | 0
1552 | LPDJD-PP-15-0034 | Construction of Judges Lodge at Larkana (Revised) Rs. 156.509 (M) Capital Rs. 27.551 (M) Revenue. | Larkano | Approved 3.12.20 | June-23 | 184.06 | 54.79 | 0.732 | 0.000 | 55.522 | 128.538 | 38.119 | 0 | 38.119 | 19.0595 | 0 | 19.0595 | [8 empty] | 19.0595 | 0 | 19.0595 | 18.8685 |  | 18.8685 | 0.19059 | 0 | 18.8527 | 18.8527 |  | Cap: 05-07-2022 & 11-08-2022 | 0
1553 | LPDJD-PP-17-0132 | Construction of Two (02) Residences for Judicial Officers / Staff Quarters at Nasirabad | Kamber | Approved 27.10.17 (U/R) | June-23 | 28.384 | 21.526 | 6.857 | 0 | 28.383 | 0.001 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1554 | LPDJD-PP-17-0133 | Construction of Five (05) No. Bungalows at Shahdadkot | Kamber | Approved 26.12.14 | June-23 | 55.966 | 0.103 | 9.897 | 0.000 | 10 | 45.966 | 30 | 0 | 30 | 15 | 0 | 15 | [8 empty] | 15 | 0 | 15 | 14.85 |  | 14.85 | 0.15 | 0 | 14.844 | 14.844 |  | Cap: 05-07-2022 & 15*02-2023 | 0
1555 | LPDJD-PP-17-0136 | Construction of One (01) Residence at Tangwani (SDG # 16) | Kashmore | Approved 27.10.17 | June-23 | 9.787 | 8.278 | 1.509 | 0 | 9.787 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1556 | LPDJD-PP-17-0137 | Construction of Three Bungalows at Gambat | Khairpur | Approved 26.12.14 (U/R) | June-23 | 32.477 | 26.689 | 5.083 | 0 | 31.772 | 0.705 | 0.705 | 0 | 0.705 | 0.3525 | 0 | 0.3525 | [8 empty] | 0.3525 | 0 | 0.3525 | 0.17449 |  | 0.17449 | 0.0017625 | 0 | 0 | 0 |  | Cap: 05-07-2022 | 0
1557 | LPDJD-PP-17-0140 | Construction of Judges Bungalow (01 No.) Thana Bula Khan (SDG # 16) | Jamshoro | Approved 25.08.21 | June-23 | 15.81 | 10.735 | 0.002 | 0 | 10.737 | 5.073 | 5.073 | 0 | 5.073 | 5.073 | 0 | 5.073 | [8 empty] | 5.073 | 0 | 5.073 | 5.0226 |  | 5.0226 | 0.050682 | 0 | 4.7255 | 4.7255 |  | Cap: 05-07-2022& 29-07-2022 | 0
1558 | LPDPC-PP-08-0003 | Construction of officers/officials residential accommodation for the prosecutors in Sindh (SDG # 16) | Sindh | Approved 27.08.08 | June-24 | 359.161 | 130.688 | 0 | 0 | 130.688 | 228.473 | 15 | 0 | 15 | 7.5 | 0 | 7.5 | [8 empty] | 7.5 | 0 | 7.5 |  |  | 0 |  | 0 | 0 | 0 | MEC Un-Satisfactory |  | 0
|  | Total Judicial GSH (Ongoing) :- |  |  |  | 1678.287 | 1037.46 | 144.797 | 0 | 1182.257 | 496.03 | 88.9 | 87.274 | 176.174 | 46.9865 | 87.274 | 134.2605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.9865 | 87.274 | 134.2605 | 38.9155 | 87.274 | 126.1895 | 0.39304 | 0 | 38.4222 | 38.4222 |  |  | 0
JUDICIAL
Government Servant Housing
(New Schemes)
1559 | LPDJD-PP-18-0019 | Construction of Residential Complex for Officers / Officials of High Court of Sindh at Milk Plant | Karachi | Un-Approved | June-23 | 1383.424 | 0 | 0 | 0.000 | 0 | 1383.424 | 345.856 | 0 | 345.856 | 172.928 | 0 | 172.928 | [8 empty] | 172.928 | 0 | 172.928 | 171.198 |  | 171.198 | 1.73 | 0 | 171.198 | 171.198 |  | Cap: 27-03-2023 & 10-04-2023 | 0
1560 | LPDJD-PP-21-0588 | Const: of Huts/Rest House for the Honorable Judges of Honorable Sindh High Court of Hawks bay. | Karachi | Un-Approved | June-24 | 50 | 0 | 0 | 0.000 | 0 | 50 | 12.5 | 0 | 12.5 | 6.25 | 0 | 6.25 | [8 empty] | 6.25 | 0 | 6.25 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
1561 | LPDJD-PP-22-0581 | Construction of Residences for Judicial Officers at Umerkot (05 Nos.) | Umerkot | Un-Approved | June-25 | 91.111 | 0 | 0 | 0 | 0 | 91.111 | 22.7778 | 0 | 22.7778 | 11.3889 | 0 | 11.3889 | [8 empty] | 11.3889 | 0 | 11.3889 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
|  | Total Judicial GSH (New) :- |  |  |  | 1524.535 | 0 | 0 | 0 | 0 | 1524.535 | 381.1338 | 0 | 381.1338 | 190.5669 | 0 | 190.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190.5669 | 0 | 190.5669 | 171.198 | 0 | 171.198 | 1.73 | 0 | 171.198 | 171.198 |  |  | 0
|  | Total Judicial GSH(New+On-going:- |  |  |  | 3202.822 | 1037.46 | 144.797 | 0 | 1182.257 | 2020.565 | 470.0338 | 87.274 | 557.3078 | 237.5534 | 87.274 | 324.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237.5534 | 87.274 | 324.8274 | 210.1135 | 87.274 | 297.3875 | 2.123 | 0 | 209.6202 | 209.6202 |  |  | 0
Government Office Building
(On-Going Schemes)
1562 | LPDJD-PP-16-0070 | Construction of New Annexe Building No. I & II (Re-Re-Revised) (C:897.717+R:60.230) | Karachi | Approved 02.02.17 | June-24 | 957.947 | 797.334 | 0.25 | 0 | 797.584 | 160.363 | 1 | 0.8 | 1.8 | 0.5 | 0.4 | 0.9 | [8 empty] | 0.5 | 0.4 | 0.9 | 0.2475 |  | 0.2475 | 0.0025 | 0 | 0 | 0 |  | Cap: 05-07-2022 | 0
1563 | LPDJD-PP-11-0019 | Construction of District Court Building at Kamber (Re-Revised) | Kamber | Approved 2018 | June-24 | 257.81 | 252.285 | 0.341 | 0 | 252.626 | 5.184 | 5.184 | 0 | 5.184 | 5.184 | 0 | 5.184 | [8 empty] | 5.184 | 0 | 5.184 | 5.132 |  | 5.132 | 0.05196 | 0 | 5.0296 | 5.0296 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1564 | LPDJD-PP-15-0035 | Construction of District Court Building at Kashmore at Kandhkot (Revised) | Kashmore | Approved 25.11.15 (U/R) | June-24 | 134.555 | 134.999 | 0 | 0 | 134.999 | -0.444 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001
1565 | LPDJD-PP-07-0007 | Provision of Bar Room & Library in Judl: Distt: across the Sindh | Sindh | Approved 24.04.08 (U/R) | June-24 | 87.213 | 91.969 | 0 | 0 | 91.969 | -4.756 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1566 | LPDJD-PP-09-0006 | Constt: of Bar Room, Library, Canteen and Litigants / Vehicles Sheds at High Court Circuit Bench, Larkano (SDG # 16) | Larkano | Approved 11.05.10 (U/R) | June-24 | 45.556 | 45.3993 | 0.117 | 0 | 45.5162 | 0.03975 | 0.04 | 0 | 0.04 | 0.02 | 0 | 0.02 | [8 empty] | 0.02 | 0 | 0.02 |  |  | 0 |  | 0 | 0 | 0 | Under Revision |  | 0
1567 | LPDJD-PP-19-0195 | Construction of Four (04) No. Courts at Pano Aqil.(Revised) | Sukkur | Approved 10.07.19 | June-24 | 95.99 | 19.097 | 38.447 | 0 | 57.544 | 38.446 | 38.446 | 0 | 38.446 | 38.446 | 0 | 38.446 | [8 empty] | 38.446 | 0 | 38.446 | 38.0614 |  | 38.0614 | 0.38411 | 0 | 0 | 0 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1568 | LPDJD-PP-17-0142 | Construction of (04 Nos) Courts Ratodero (Revised) (SDG# 16) | Larkano | Approved 23.2.18 (U/R) | June-24 | 179.955 | 94.463 | 85.49 | 0 | 179.953 | 0.002 | 0.002 | 0 | 0.002 | 0.001 | 0 | 0.001 | [8 empty] | 0.001 | 0 | 0.001 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.002 |  | 0
1569 | LPDJD-PP-13-0024 | Construction of Courts (2 Nos.) at Sakrand (SDG # 16) | S.B.A | Approved 17.04.14 | June-23 | 44.386 | 43.256 | 0.283 | 0 | 43.539 | 0.847 | 0.847 | 0 | 0.847 | 0.847 | 0 | 0.847 | [8 empty] | 0.847 | 0 | 0.847 | 0.83863 |  | 0.83863 | 0.0081175 | 0 | 0.417 | 0.417 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1570 | LPDJD-PP-12-0037 | Construction of Judicial Complex Tharparkar Mithi | Tharparkar | Approved 03.05.13 (U/R) | June-24 | 300.2 | 300.074 | 0.032 | 0 | 300.106 | 0.094 | 0.094 | 0 | 0.094 | 0.047 | 0 | 0.047 | [8 empty] | 0.047 | 0 | 0.047 |  |  | 0 |  | 0 | 0 | 0 | Under Revision |  | 0
1571 | LPDJD-PP-15-0036 | Construction of 3 Nos. Courts Matli (C:89.831+R:2.364) | Badin | Approved 07.09.16 (U/R) | June-24 | 92.195 | 92.195 | 0 | 0 | 92.195 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1572 | LPDJD-PP-16-0071 | Construction of Court Building at Kunri, Samaro & Pitharo (1 No. Each) | Umerkot | Approved 07.09.16 (U/R) | June-24 | 93.552 | 93.543 | 0.00225 | 0 | 93.5453 | 0.00675 | 0.007 | 0 | 0.007 | 0.007 | 0 | 0.007 | [8 empty] | 0.007 | 0 | 0.007 | 0.0067325 |  | 0.0067325 | 1.8e-05 | 0 | 0 | 0 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1573 | LPDJD-PP-16-0073 | Construction of Judicial Complex at Sanghar ( 06 Nos. Courts) | Sanghar | Approved 07.09.16 (U/R) | June-24 | 99.879 | 99.829 | 0 | 0 | 99.829 | 0.05 | 0.05 | 0 | 0.05 | 0.025 | 0 | 0.025 | [8 empty] | 0.025 | 0 | 0.025 |  |  | 0 |  | 0 | 0 | 0 | Under Revision |  | 0
1574 | LPDJD-PP-16-0074 | Construction of Courts Building (04 Nos.) (02 Nos. at Johi, 01 No. at K.N. Shah, 01 No. at Mehar) | Dadu | Approved 07.09.16 (U/R) | June-24 | 99.918 | 99.918 | 0 | 0 | 99.918 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1575 | LPDJD-PP-16-0075 | Construction of 01 Court Building at Taluka Mehrabpur, District Naushehro Feroze | N. Feroze | Approved 07.09.16 (U/R) | June-24 | 32.998 | 32.998 | 0 | 0 | 32.998 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1576 | LPDJD-PP-16-0076 | Construction of Two Courts Building (1 ADJ & 1 SCJ) (SDG # 16) | S.B.A | Approved 07.09.16 | June-23 | 44.041 | 44.041 | 0 | 0 | 44.041 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 (Un-Satisfactory) |  | 0
1577 | LPDJD-PP-16-0077 | Construction of Four (04) Court Building @ Naushehro Feroze (2 ADJs & 2 JMs) | N. Feroze | Approved 07.09.16 (U/R) | June-24 | 85.625 | 80.299 | 5.326 | 0 | 85.625 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1578 | LPDJD-PP-16-0078 | Construction of Two Court Building at District Ghotki (1 ADJs & 1 JM) | Ghotki | Approved 07.09.16 (U/R) | June-24 | 48.397 | 46.079 | 2.169 | 0 | 48.248 | 0.149 | 0.149 | 0 | 0.149 | 0.0745 | 0 | 0.0745 | [8 empty] | 0.0745 | 0 | 0.0745 |  |  | 0 |  | 0 | 0 | 0 | Under Revision |  | 0
1579 | LPDJD-PP-16-0079 | Construction of Car Parking/Conference Hall/Offices/Courts/depression portion at District Court Sukkur | Sukkur | Approved 25.11.16 (U/R) | June-24 | 129.613 | 70.556 | 59.0565 | 0 | 129.6125 | 0.0005 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1580 | LPDJD-PP-17-0143 | Construction of 34 No. Courts at District Korangi. Cap: Rs. 2220.366 (M) , Rev: Rs. 47.236 (M) | Karachi | Approved 06.04.18 | June-24 | 2267.602 | 267.5 | 393.4547 | 0 | 660.9547 | 1606.6472 | 524 | 0 | 524 | 524 | 0 | 524 | [6 empty] | 300 |  | 824 | 0 | 824 | 815.758 |  | 815.758 | 8.242 | 0 | 815.758 | 815.758 | Rs. 300 (M) adopted from Over all Saving | Cap: 05-07-2022 & 11-08-2022 & 22-09-2022 & 20-01-2023 | 0
1581 | LPDJD-PP-17-0144 | Construction of Judicial Complex at Sujawal (06 No. Courts) | Sujawal | Approved 12.01.18 | June-24 | 150.011 | 25.43 | 40 | 0 | 65.43 | 84.581 | 30 | 0 | 30 | 15 | 0 | 15 | [6 empty] | 15 |  | 30 | 0 | 30 | 29.7 |  | 29.7 | 0.3 | 0 | 12.1286 | 12.1286 | Rs. 15 (M) adopted from Over all saving | Cap: 05-07-2022 & 21-12-2022 & 17-02-2023 & 01-03-2023 | 0
1582 | LPDJD-PP-17-0145 | Construction of Two (02) Court Building at Nasirabad (Revised) | Kamber | Approved 25.08.21 | June-24 | 80.678 | 21.526 | 0 | 0 | 21.526 | 59.152 | 59.152 | 0 | 59.152 | 59.152 | 0 | 59.152 | [8 empty] | 59.152 | 0 | 59.152 | 58.56 |  | 58.56 | 0.592 | 0 | 11.4202 | 11.4202 |  | Cap: 05-07-2022 | 0
1583 | LPDJD-PP-17-0146 | Construction of Five (05) Court Building at Shahdadkot | Kamber | Approved 16.01.18 (U/R) | June-24 | 141.064 | 43.659 | 24.351 | 0 | 68.01 | 73.054 | 73.054 | 0 | 73.054 | 73.054 | 0 | 73.054 | [8 empty] | 73.054 | 0 | 73.054 | 72.3239 |  | 72.3239 | 0.73064 | 0 | 72.3223 | 72.3223 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1584 | LPDJD-PP-17-0147 | Construction of Two (02) Courts at MiroKhan | Kamber | Approved 27.10.17 (U/R) | June-24 | 48.833 | 41.819 | 7.005 | 0 | 48.824 | 0.009 | 0.009 | 0 | 0.009 | 0.009 | 0 | 0.009 | [8 empty] | 0.009 | 0 | 0.009 | 0.0092275 |  | 0.0092275 | 2.25e-05 | 0 | 0 | 0 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1585 | LPDJD-PP-17-0148 | Construction of Two (02) Courts at Tangwani | Kashmore | Approved 27.10.17 (U/R) | June-24 | 48.833 | 35.552 | 13.281 | 0 | 48.833 | 0 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1586 | LPDJD-PP-17-0149 | Construction of One Court at Nara (SDG # 16) | Khairpur | Approved 27.10.17 | June-23 | 38.319 | 30 | 7.876 | 0 | 37.876 | 0.443 | 0.443 | 0 | 0.443 | 0.2215 | 0 | 0.2215 | [8 empty] | 0.2215 | 0 | 0.2215 |  |  | 0 |  | 0 | 0 | 0 | MEC Un-Satisfactory |  | 0
1587 | LPDJD-PP-17-0150 | Const. of 2 Court Building at Khipro (Revised) (SDG # 16) | Sanghar | Approved 25.08.221 | June-23 | 79.69 | 52.897 | 0 | 0 | 52.897 | 26.793 | 26.793 | 0 | 26.793 | 26.793 | 0 | 26.793 | [8 empty] | 26.793 | 0 | 26.793 | 26.525 |  | 26.525 | 0.268 | 0 | 25 | 25 |  | Cap: 05-07-2022 | 0
1588 | LPDJD-PP-19-0196 | Construction of additional Court / Record Room for District West and Extension of Bar Room (Revised) (C:300.742+R:32.815) (SDG # 16) | Karachi | Approved 10.03.20 | June-23 | 333.557 | 255.921 | 77.636 | 0 | 333.557 | 0 | 0 | 32.815 | 32.815 | 0 | 16.4075 | 16.4075 | [8 empty] | 0 | 16.4075 | 16.4075 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
1589 | LPDJD-PP-19-0197 | Const. of Judicial Academy City Campus at Bungalow No. 1 & 2, Bath Island Karachi (Cap: 275.677 + Rev: 35.962 ) | Karachi | Approved 27.01.20 | June-24 | 311.639 | 3.029 | 120 | 0 | 123.029 | 188.61 | 31.476 | 0 | 31.476 | 31.476 | 0 | 31.476 | [8 empty] | 31.476 | 0 | 31.476 | 31.1603 |  | 31.1603 | 0.31738 | 0 | 31.158 | 31.158 |  | Cap: 05-07-2022 & 11-08-2022 & 22-09-2022 | 0
1590 | LPDJD-PP-19-0198 | Rehabilitation of Old Sessions Court Building / Re-Construction of Compound Wall and External Work at Judicial Complex District Badin (Revised) | Badin | Approved 25.08.21 | June-23 | 72.95 | 12.065 | 30.443 | 0 | 42.508 | 30.442 | 30.442 | 0 | 30.442 | 30.442 | 0 | 30.442 | [8 empty] | 30.442 | 0 | 30.442 | 30.137 |  | 30.137 | 0.304 | 0 | 30.1356 | 30.1356 |  | Cap: 05-07-2022 & 29-07-2022 | 0
1591 | LPDJD-PP-19-0199 | Construction of Record Room alongwith Store Room & Provision of Elevator / Lift Facilities and Construction of Cafeteria at High Court Circuit, Larkana (Cap: 57.00 + Rev: 2.100) | Larkano | Approved 04.10.19 | June-24 | 59.1 | 1.563 | 21.757 | 0 | 23.32 | 35.78 | 33.68 | 2.1 | 35.78 | 33.68 | 2.1 | 35.78 | [8 empty] | 33.68 | 2.1 | 35.78 | 33.3428 |  | 33.3428 | 0.3372 | 0 | 3.1526 | 3.1526 | Un-Satisfactory | Cap: 05-07-2022 & 29-07-2022 | 0
1592 | LPDJD-PP-21-0589 | Construction of Bar Room, Bar Library and Additional ten (10) No. Courts at District Court Building, Malir(Cap: 241.368 + Rev: 39.373) | Karachi (Malir) | Approved 04.01.22 | June-24 | 280.741 | 0 | 163.486 | 0 | 163.486 | 117.255 | 40 | 0 | 40 | 40 | 0 | 40 | 25 | [7 empty] | 65 | 0 | 65 | 64.6 |  | 64.6 | 0.4 | 0 | 64.35 | 64.35 | Rs. 25 (M) adopted through re-app: | Cap: 05-07-2022 & 11-08-2022 & 22-09-2022 & 26-05-2023 | 0
1593 | LPDPC-PP-07-0008 | Construction of offices for the Prosecutors in Sindh. (22 Nos) (SDG # 16) | Sindh | Approved 13.06.08 (U/R) | June-24 | 256.826 | 215.081 | 0 | 0 | 215.081 | 41.745 | 20 | 0 | 20 | 10 | 0 | 10 | [8 empty] | 10 | 0 | 10 |  |  | 0 |  | 0 | 0 | 0 | MEC Un-Satisfactory |  | 0
1594 | LPDPC-PP-19-0202 | Construction of Prosecution Office, Hyderabad over 8 Court Building 5th Floor. (SDG # 16) | Hyderabad | Approved 04.02.20 | June-24 | 45 | 0 | 42.081 | 0 | 42.081 | 2.919 | 2.919 | 4.636 | 7.555 | 2.919 | 4.636 | 7.555 | [8 empty] | 2.919 | 4.636 | 7.555 |  |  | 0 |  | 0 | 0 | 0 | Throeforward & Aloocation not match |  | 0
1595 | LPDBG-PP-19-0203 | Construction of Administration Block of Government of Sindh Law College, Hyderabad. (Cap. 51.009 + Rev. 8.901) | Hyderabad | Approved 04.02.20 | June-24 | 60 | 0 | 15 | 0 | 15 | 45 | 36.099 | 8.901 | 45 | 36.099 | 8.901 | 45 | [8 empty] | 36.099 | 8.901 | 45 | 35.738 |  | 35.738 | 0.361 | 0 | 29.2577 | 29.2577 |  | Cap: 05-07-2022 | 0
MISSING / PHASED OUT
1596 | LPDJD-PP-22-0582 | Construction of Courts (8 Nos.) at District Huderabad (ADP # ) | Hyderabad | Approved | June-23 | 37.715 | 65 | 0 | 0 | 65 | -27.285 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Throeforward over & Above |  | 0
1597 | LPDJD-PP-22-0583 | Consrructon of one Court Building at Sujawal shifted ot Garho (Missing Scheme) (ADP # ) | Thatta | Approved | June-23 | 50.07 | 0 | 0 | 0 | 0 | 50.07 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1598 | LPDJD-PP-22-0584 | Consrructon of one Court Building at Thana Bula Khan i/c compound wall (Missing scheme) (ADP# 1020 /2018-19) | Jamshoro | Approved | June-23 | 12.833 | 0 | 0 | 0 | 0 | 12.833 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
1599 | LPDJD-PP-22-0585 | Construciton of underground car parking and Auditorium Hall at High Court Circuit Bench Hyderabad. | Hyderabad | Approved | June-23 | 21.585 | 0 | 0 | 0 | 0 | 21.585 | 0.001 | 0 | 0.001 | 0.0005 | 0 | 0.0005 | [8 empty] | 0.0005 | 0 | 0.0005 |  |  | 0 |  | 0 | 0 | 0 | Tokin Amount Rs. 0.001 |  | 0
|  | Total Judicial (GOB) (Ongoing) :- |  |  |  | 7226.876 | 3509.3763 | 1147.8845 | 0 | 4657.2608 | 2569.6153 | 953.899 | 49.252 | 1003.151 | 928.0035 | 32.4445 | 960.448 | 25 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 1268.0035 | 32.4445 | 1300.448 | 1242.1405 | 0 | 1242.1405 | 12.2989 | 0 | 1100.1295 | 1100.1295 |  |  | 0
Government Office Building
(New Schemes)
1600 | LPDJD-PP-21-0590 | Provision of Furniture & Fixture throughout Sindh (59 Nos.) (Phase-I). | Sindh | Un-Approved | June-25 | 186.62 | 0 | 0 | 0 | 0 | 186.62 | 46.655 | 0 | 46.655 | 23.3275 | 0 | 23.3275 | [8 empty] | 23.3275 | 0 | 23.3275 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
1601 | LPDJD-PP-21-0591 | Conversion of Old Annexe Building into 12 Court Building for High Court of Sindh Karachi. Rs. 100 (M) for Capital Work Rs. 100 (M) for Revenue Component | Karachi | Un-Approved | June-25 | 200 | 0 | 0 | 0 | 0 | 200 | 50 | 0 | 50 | 25 | 0 | 25 |  | 25 | [6 empty] | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | Rs/ 25 (M) re-app; to ADP 1592 on 26-05-2023 |  | 0
1602 | LPDJD-PP-22-0586 | Construction of 03 Nos. Court Building at Dokri (District Larkana) (C:142.699+R:13.5) | Larkano | Un-Approved | June-25 | 156.199 | 0 | 0 | 0 | 0 | 156.199 | 39.0498 | 0 | 39.0498 | 19.5249 | 0 | 19.5249 | [8 empty] | 19.5249 | 0 | 19.5249 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
1603 | LPDJD-PP-22-0587 | Construction of Three (03) No. Court Buildings at Digri (C:104.170+13.50) | Larkano | Un-Approved | June-25 | 117.67 | 0 | 0 | 0 | 0 | 117.67 | 29.4175 | 0 | 29.4175 | 14.7088 | 0 | 14.7088 | [8 empty] | 14.7088 | 0 | 14.7088 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
1604 | LPDJD-PP-22-0588 | Construction of One Court Building at Lakhi Ghulam Shah and one Court at Khanpur (District Shikarpur) Civil 128.676 Rev 09.00 (M) | Shikarpur | Un-Approved | June-25 | 137.676 | 0 | 0 | 0 | 0 | 137.676 | 34.419 | 0 | 34.419 | 17.2095 | 0 | 17.2095 | [8 empty] | 17.2095 | 0 | 17.2095 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0
|  | Total Judicial (GOB) (New) :- |  |  |  | 798.165 | 0 | 0 | 0 | 0 | 798.165 | 199.5412 | 0 | 199.5412 | 99.7706 | 0 | 99.7706 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 74.7706 | 0 | 74.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | Total Judicial (GOB) :- |  |  |  | 8025.041 | 3509.3763 | 1147.8845 | 0 | 4657.2608 | 3367.7803 | 1153.4402 | 49.252 | 1202.6922 | 1027.7741 | 32.4445 | 1060.2186 | 25 | 25 | 0 | 0 | 0 | 0 | 315 | 0 | 1342.7741 | 32.4445 | 1375.2186 | 1242.1405 | 0 | 1242.1405 | 12.2989 | 0 | 1100.1295 | 1100.1295 |  |  | 0
|  | Total Law (On-going) |  |  |  | 8905.163 | 4546.8363 | 1292.6815 | 0 | 5839.5178 | 3065.6453 | 1042.799 | 136.526 | 1179.325 | 974.99 | 119.7185 | 1094.7085 | 25 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 1314.99 | 119.7185 | 1434.7085 | 1281.056 | 87.274 | 1368.33 | 12.692 | 0 | 1138.5518 | 1138.5518 |  |  | 0
|  | Total Law (New) |  |  |  | 2322.7 | 0 | 0 | 0 | 0 | 2322.7 | 580.675 | 0 | 580.675 | 290.3375 | 0 | 290.3375 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 265.3375 | 0 | 265.3375 | 171.198 | 0 | 171.198 | 1.73 | 0 | 171.198 | 171.198 |  |  | 0
|  | Total Law, P.A & Prosecution Deptt :- |  |  |  | 11227.863 | 4546.8363 | 1292.6815 | 0 | 5839.5178 | 5388.3453 | 1623.474 | 136.526 | 1760 | 1265.3275 | 119.7185 | 1385.046 | 25 | 25 | 0 | 0 | 0 | 0 | 315 | 0 | 1580.3275 | 119.7185 | 1700.046 | 1452.254 | 87.274 | 1539.528 | 14.422 | 0 | 1309.7498 | 1309.7498 |  |  | 0